## Sheet1
Sprint NB | issue title | Description | Status | Assignee
Sprint 3 | Account content referesh | The download managers and the data access requests are loaded when the account menu is clicked and they are not there are two possibilities: 1- add a refresh button-2-recreate the view when the tab is clicked but it is not really obvious since the the tabs are created in the bigging on hidden/shown afterwards.-3-add a timeout to the models (download managers/Dars) fetch methods, the time out could be a configurable value. | Open | EM
Sprint 3 | widget styling | Change the headers to be in the top of the widget rather inside the widget content. | Open | EM
Sprint 3 | popup widgets | not use jqm popups but a custom component to allow closing the widget. | Open | EM
|  | But if the JQM is upgraded the dismissable property is added so it can be used-to be decided |  | EM
Sprint 3 | open search url for search | According to specs the user has the possibility to enter his own open search url. For the moment it is not possible | Open | EM
Sprint 3 | selected download options | The selected download options are not set when opening the STO widget | Open | EM
Sprint 3 | seconds handling in dates widgets | The timebox/datebox plugin does not allow seconds choice. However, the seconds are added by the client to be 00. For the moment, we have decided to use the plugin as it is. | Open
Sprint 3 | map display | In 2D mode, the map can be dragged untill seeing the eadges of the map | Open