## Sheet1
Sprint NB | issue title | Description | Status | Assignee
Sprint 3 | Account content referesh | The download managers and the data access requests are loaded when the account menu is clicked and they are not there are two possibilities: 1- add a refresh button-2-recreate the view when the tab is clicked but it is not really obvious since the the tabs are created in the bigging on hidden/shown afterwards.-3-add a timeout to the models (download managers/Dars) fetch methods, the time out could be a configurable value. | Open | EM
Sprint 3 | widget styling | Change the headers to be in the top of the widget rather inside the widget content. | Done | FL
Sprint 3 | popup widgets | not use jqm popups but a custom component to allow closing the widget.But if the JQM is upgraded the dismissable property is added so it can be used-to be decided | Done | FL
Sprint 3 | Enter openSearch url for search | According to specs the user has the possibility to enter his own open search url. For the moment it is not possible | Open | FL
Sprint 3 | selected download options | The selected download options are not set when opening the STO widget | Done | EM
Sprint 3 | map display | In 2D mode, the map can be dragged untill seeing the eadges of the map | Done | FL
Sprint 4 | Error message | An error message should be displayed when the server does not answer, or does not answer correctly | Done | EM
CDR | Product Download | Diffenriate between Direct Download and Download with Local DM | Open
CDR | Browse URL | What we should expect ? | Open
CDR | Name/Description in DataSet Selection |  | Open
CDR | Paging issue | Automatic ? Manual ? | Open
CDR | Granule representation in the Web Client |  | Open